LAB REPORT

Software Project Management

Student Name: Nguyễn Văn Minh

ID: 22003405

Class: DHKTPM18

Course: 2025-2026

Contents

Module 1:	3

Exercise 1: Creating a link	3

Exercise 2: Setting duration	3

Exercise 3: Creating phases	4

Exercise 4: Noah - Linking	5

Exercise 5: Pyramid - Multi level grouping	6

Exercise 6: Creating a plan for Staff Training	7

Exercise 7: Recurring Tasks	8

Exercise 8: Travelling – tasks calendar	9

Module 2:	10

Exercise 1: Part Time - creating new calendar	10

Exercise 2: Changing Working Time	15

Exercise 3: Changing Working Time	20

Exercise 4: Changing Working Time	24

Exercise 5: Create the private Time for a project	27

Exercise 6: My project	31

Module 3: Working with Tasks	33

Exercise 1: Changing Working Time (Start Date Feb 2st 2026)	33

Exercise 2: Changing Working Time (Start Date Feb 2rd 2026)	35

Exercise 3: Scheduling – Task dependencies	37

Module 4: Assigning resources to the tasks in Project	41

Exercise 1: Entering Resources	41

Exercise 2: Entering resources	42

Exercise 3: Entering resources	43

Exercise 4: Entering resources	44

Exercise 5: Resources with the private working time	46

Exercise 6: The Engagement planning	48

Module 5: COST, CONSTRAINS, DEADLINE for TASKs	51

Exercise 1: Entering Cost	51

Exercise 2:	52

Exercise 3:	53

Exercise 4:	54

Module 6:	57

Exercise 1:	57

# Module 1:

## Exercise 1: Creating a link

## Exercise 2: Setting duration

## Exercise 3: Creating phases

## Exercise 4: Noah - Linking

## Exercise 5: Pyramid - Multi level grouping

## Exercise 6: Creating a plan for Staff Training

## Exercise 7: Recurring Tasks

## Exercise 8: Travelling – tasks calendar

Travelling – task calendar You intend to travel from HCM to Kuala Lumpur, Bangkok and then, come back to HCM. Creating a plan for your trip.

# Module 2:

## Exercise 1: Part Time - creating new calendar

Part Time - creating new calendar 
Open project file Ex2 (Module 1), Use the Project Information dialog box to:

A part-time worker will be used on this project. Go to the Change Working Time dialog box and create a new copy of the Standard calendar, calling it "Part Time".

Update the working time of your new calendar so that: 
 Mondays to Fridays are nonworking time 
 The remaining 2 weekdays have working time of 10:00 to 16:00 ( no breaks)

The Part time has also booked a holiday from 1st to Feb 5th . Create an Exception to their calendar with a Holiday name and these days as nonworking

Display the Project Information.

## Exercise 2: Changing Working Time

Changing Working Time

Open project file Ex4 (Module 1) Use the Project Information dialog box to:

Start Date: Nov 20th 2025

Go to the Change Working Time dialog box and create an Exception called "Tet Holidays" during from Dec 24th 2026 to Jan 5th 2026 into nonworking time.

Change Work Weeks time of Standard calendar's default working week. This project's standard working time are:

08:30 to 17:30 Monday to Thursday (no lunch break)

08:30 to 16:00 on Fridays (no lunch break)

Add a new Work Week to the Standard calendar named "Xmas Slowdown". Use this to model a 12:30 finish on every weekday from Dec 10th 2025 to Dec 23rd 2025.

Capture the Work weeks time

## Exercise 3: Changing Working Time

Open project file Ex5 (Module 1), Use the Project Information dialog box to:

Star Date: Apr 5th 2026

The office will shut down for 2 weeks in the summer. Use the Change Working Time dialog box to create an Exception called "Summer Shutdown" and make the first 14 workdays of August nonworking time

Create an Exception called “Independence Days” is 2 Sep nonworking time.

Create an Exception called “International Labor days” is Apr 30th and May 1st nonworking time

Display the Project Information

## Exercise 4: Changing Working Time

Open project file Ex6 (Module 1), Use the Project Information dialog box to:

Modify the Standard calendar and change the [Default] work week to use the hours shown below:

Add an exception in the Standard calendar called Recovery with in 7 lates workdays of March is non-working days.

Display the Project Information.

## Exercise 5: Create the private Time for a project

Open project file Ex7 (Module 1), Use the Project Information dialog box to:

Create the new Time Work for your project.

[NameTimeProject] {Name: Your Name - Ex: MinhTimeProject}

Change Work Weeks time of Standard calendar's default working week. This project's standard working time are:

08:00 to 12:00 on Mon, Wed, Fri

13:00 to 16:00 on Tue, Thu, Sat

Create an Exception called “International Labor days” is Apr 30th and May 1st nonworking time

Capture the Work weeks time

## Exercise 6: My project

Create your plan from Monday to Sunday. It will list all of your activities, your time you spend and resources joining in each task.

Create a new calendar called Student based on the Standard calendar.

Change the [Default] work week so that the hours match to your calendar everyday

Using Note function in MP 2010 to take note for important tasks in your plan.

# Module 3: Working with Tasks

## Exercise 1: Changing Working Time (Start Date Feb 2st 2026)

Display the Project Information.

View Project Timeline

Gantt Chart

view CP

Total Slack

## Exercise 2: Changing Working Time (Start Date Feb 2rd 2026)

Timeline

Gantt Chart

view CP

Total Slack

## Exercise 3: Scheduling – Task dependencies

Display the Project Information.

View the project in Gantt Chart and define CP and Project Slack

Choose Gantt Chart Format tab  check on Critical Tasks in Bar Styles.

On the table data Add column Late Start, Late Finish, Total Slack

# Module 4: Assigning resources to the tasks in Project

## Exercise 1: Entering Resources

- Gantt Chart

- Display the Project Information (Statics): Duration, Hours, Cost

- Resource Sheet

- Resource Usage

## Exercise 2: Entering resources

- Gantt Chart (Resource Name, Cost Column)

- Display the Project Information (Statics): Duration, Hours, Cost

- Resource Sheet

- Resource Usage

## Exercise 3: Entering resources

- Gantt Chart (Resource Name, Cost Column)

- Display the Project Information (Statics): Duration, Hours, Cost

- Resource Sheet

- Resource Usage

## Exercise 4: Entering resources

- Gantt Chart (Resource Name, Cost Column)

- Display the Project Information (Statics): Duration, Hours, Cost

- Resource Sheet

- Resource Usage

## Exercise 5: Resources with the private working time

Capture images:

- Gantt Chart (Resource Name, Cost Column)

- Display the Project Information (Statics): Duration, Hours, Cost

- Resource Sheet

- Resource Usage

## Exercise 6: The Engagement planning

Capture images:

- Gantt Chart (Resource Name, Cost Column)

- Display the Project Information (Statics): Duration, Hours, Cost

- Resource Sheet - Resource Usage

# Module 5: COST, CONSTRAINS, DEADLINE for TASKs

## Exercise 1: Entering Cost

## Exercise 2:

## Exercise 3:

## Exercise 4:

Cost of project? 

Update Project after 1 month?

Update Project after 4,5 month? Cost of Project? 

Update Project after 6 month? Cost of Project?

# Module 6:

## Exercise 1: